## TPCS Project
TPCS WordPress App Deployment on AWS
Project Name | WordPress with RDS Deployment on Amazon AWS
Project Manager | Manoj | [5 empty] | Project Legend
Project Consultant | Mounika,Sirisha,Bipeen | [5 empty] | Not Started
Start Date | 2020-06-27 | [5 empty] | Inprogress
End Date | 2020-06-28 | [5 empty] | Completed
Project Phase | Project Tasks | Start Date | End Dtae | Status | Assigned | Remark
Planning Phase
| Understand the Customer Requirement | 2020-06-27 | 2020-06-27 |  | Manoj
| Design The Logical Architecture- HLD | 2020-06-27 | 2020-06-27 |  | Manoj
| Create an UAT Plan | 2020-06-27 | 2020-06-27 |  | Manoj
| Create a Project Plan (WBS) | 2020-06-27 | 2020-06-27 |  | Manoj
| Create a Low Level design (LLD)- Technical Execution Document | 2020-06-27 | 2020-06-27 |  | Bipeen + Monika+Sirisha
Build Phase
| Create a AWS Account for TPCS | 2020-06-27 | 2020-06-27 |  | Manoj | DONE
| Set the Region | 2020-06-27 | 2020-06-27 |  | Manoj | MUMBAI
| Define the Login Account | 2020-06-27 | 2020-06-27 |  | Manoj | Create login account for sirisha,mounika,bipeen
| Create IAM Roles | 2020-06-27 | 2020-06-27 |  | Manoj | Created a group and assigned ec2 full permission,rds full permission and s3 read only
| Check the permission using policy simulator |  |  |  |  | https://policysim.aws.amazon.com
| Create a security group |  |  |  |  | Open ALL Ports
| Create a MySQL database for your WordPress site | 2020-06-27 | 2020-06-28 |  |  | RDS Instance is created with database name wordpress
| • Configure connectivity and network configuration for RDS Instance | 2020-06-27 | 2020-06-28
| • Create an EC2 Instance | 2020-06-27 | 2020-06-28 |  |  | create amazon linux instance
| • Allow your EC2 instance to access your RDS database | 2020-06-27 | 2020-06-28
| • Create a database user for your WordPress application and give it permission to access | 2020-06-27 | 2020-06-28 |  |  | create database user wordpress and password is Tpcs123456
| the “wordpress” database | 2020-06-27 | 2020-06-28
| • Installing the Apache web server on EC2 | 2020-06-27 | 2020-06-28
| • download the WordPress software and set up the configuration on EC2 | 2020-06-27 | 2020-06-28
| • Deploying WordPress | 2020-06-27 | 2020-06-28
| • Explore your new web site | 2020-06-27 | 2020-06-28
UAT Phase | Access the Wordpress App from Outside
Login on Wordpress App
Perform the general Task
Stablization and HandoverPhase | Training the IT team how to Handle services in AWS
Handover the Documents
Handover the Credential

## Sheet1
| AWS | Azure | Google |  |  | 35 Year
Experience | 21 | 8.5 | 12.5 |  |  | Msoffice
Cost | 10 | 12.5 | 4.5 |  | AWS | Windws 10
Full Compatibily | Windows server | Windows server | Windows server |  |  | Windows server
| SQL | SQL | SQL |  |  | SQL
| Dymanic | Dymanic | Dymanic |  |  | Dymanic
| Exchange | Exchange | Exchange |  |  | Exchange
Relationship | New | Exiting | New | java
Agreement | Agreement | Agrement |  |  |  | 99.9
| New Paymnnet | Microsoft Azure |  |  |  | IBM
| Princing | Msoffice |  |  | Gartner | Dell
|  | Wino |  |  |  | HP
40%
|  | 12 Month |  |  |  | SQL
Orackle
Mysql
| Amazon | Microsoft | Google
| e-retail | Technology | Data
| AWS |  | GCP
| 100 | 100 | 100
| 95 -eretrai | 100 | 95 - data
| 5 AWS |  | 5 GCp
10-15 Company
95% - Relatin
21 Years
Pentium

## TPCS Migration Project
TPCS Server Migration to AWS
Project Name | Migration of Server to AWS Cloud
Project Goal | TPCS Has Servers Running on Premises , TPCS wants to Migrate the Server to AWS Cloud . The Server Include App Server , File Server and MySQL Databse Server
Project Manager | Manoj | [5 empty] | Project Legend
Project Consultant | Mounika,Sirisha,Bipeen | [5 empty] | Not Started
Start Date | 2020-07-05 | [5 empty] | Inprogress
End Date | 2020-07-12 | [5 empty] | Completed
Project Phase | Project Tasks | Start Date | End Dtae | Status | Assigned | Remark
Planning Phase
| Understand the Customer Requirement | 2020-07-05 | 2020-07-05 |  | Manoj
| Design The Logical Architecture- HLD | 2020-07-05 | 2020-07-05 |  | Manoj
| Create an UAT Plan | 2020-07-05 | 2020-07-05 |  | Manoj
| Create a Project Plan (WBS) | 2020-07-05 | 2020-07-05 |  | Manoj
| Create a Low Level design (LLD)- Technical Execution Document | 2020-07-05 | 2020-07-05 |  | Bipeen + Monika+Sirisha
Build Phase
| Create a AWS Account for TPCS | 2020-06-27 | 2020-06-27 |  | Manoj | DONE
| Set the Region | 2020-06-27 | 2020-06-27 |  | Manoj | MUMBAI
| Define the Login Account | 2020-06-27 | 2020-06-27 |  | Manoj | Create login account for sirisha,mounika,bipeen
| Create IAM Roles | 2020-06-27 | 2020-06-27 |  | Manoj | Created a group and assigned ec2 full permission,rds full permission and s3 read only
| Check the permission using policy simulator |  |  |  |  | https://policysim.aws.amazon.com
| Create a security group |  |  |  |  | Open ALL Ports
| Create a Centos Linux virtual machine | 2020-06-27 | 2020-06-28 |  |  | RDS Instance is created with database name wordpress
| • Configure the host name,ip and the user account | 2020-06-27 | 2020-06-28
| • Install Apache web server | 2020-06-27 | 2020-06-28 |  |  | create amazon linux instance
| • Create a windows virtual machine | 2020-06-27 | 2020-06-28
| • Install the mysql database virtual machine | 2020-06-27 | 2020-06-28 |  |  | create database user wordpress and password is Tpcs123456
| Create a file server | 2020-06-27 | 2020-06-28
Migration Phase | Perform the Assessment using MAP Tool | 2020-06-27 | 2020-06-28
| Perform the Bandwidth Aseesment | 2020-06-27 | 2020-06-28
| Perform the Cost Estimate | 2020-06-27 | 2020-06-28
Use AWS Migrate /Endure to Migrate the App Server
Migarte the MYSQL data to S3 and From S3 Migaret to RDS
| Migrate the File Server Data to EFS/S3 | 2020-06-27 | 2020-06-28
UAT Phase | Launch the App VM in AWS
Access the Mysql Database from Mysql tool
Access the EFS/S3 using browser /Mounting
Stablization and HandoverPhase | Training the IT team how to Handle services in AWS
Handover the Documents
Handover the Credential